## Sheet1
Change Request ID | Date Submitted | Submitted by | Change description | Reason | Impact analysis | Priority | Approval Status | Approved by and date
1 | 2026-07-01 | Exam department | Forget password Feature Add | Student can forget their passwords | Core feature, DB, Login UI minor change, extra time | High | pending | Under Review
2 | 2026-07-02 | Student department | Add feature to print the result files | Students want to print ther results for record keeping | DataBase, can take many working hours | Medium | Accepted | Project Manager, 02-july-2026
3 | 2026-07-03 | Exam department | Add filtering for exam dates | Student can filter dates to see their results of differents days. | Change DataBase schema, can take many working hours | Medium | pending | Under Review
4 | 2026-07-04 | Student Affairs | Add mode(day/Night) | Many students want to adjust light according to their taste | UI enhancement, time taking feature | Medium | pending | Under Review
5 | 2026-07-05 | Exam department | Report Sharing option | Students can share their reports with their parents and teachers | Important feature, coding needed, file sharing module | Medium | Accepted | Project Manager, 08-july-2026